## Sheet1
Item | Sub item | Done? | Hours est | hours max | Priority/order | Dependant items | Sum hours | Sum max hours
Pressure sensors | test 1 | y | 0.1 | 0.2 |  |  | TOTAL
Pressure sensors | test 2 | y | 0.1 | 0.2 |  |  | 193.6 | 322.8
Pressure sensors | test 3 | y | 0.1 | 0.2 |  |  | TODO
Pressure sensors | Test with resistor values and votlage sense | y | 0.5 | 1 |  |  | 0 | 0
Hall effect | Test | y | 0.5 | 1 |  |  | DONE
Hall effect | Test with magnet | y | 0.1 | 0.4 |  |  | 193.6 | 322.8
Hall effect | Get accurate using test finger and some glue | y | 2.5 | 4.5
PCB hand | solidworks changes, inc wiring holes | y | 1.5 | 2.5
CAD | Export and put acutal pcb in design | y | 1 | 1.25
PCB Hand | double check connections and routing | y | 0.75 | 1.2
PCB hand | actual pcb design done | y | 3 | 4
pots | test pots | y | 0.2 | 0.3
Hall effect | order more sensors and magnets as a contingency | y
PCB Hand | order | y | 0.2 | 0.2
hall effect sensors | design and order PCB | y | 1 | 2
CAD | put hall in design | y | 3 | 5
CAD | Put pots in design | y | 2.5 | 3.5
Wrist motor | Working 1 way coms with Teensy | y | 0.25 | 1
DC motors and controllers | Get motors working with controllers | y | 0.4 | 1
PWM extension boards | get working with motors controller boards | y | 0.5 | 1.5
Teensy | blink | y | 0.25 | 1
Wrist motor | Get 2 way coms working for wrist motor | y | 8 | 8
PCB controller | wiring eagle | y | 4 | 6
lab things | pick up resistors from lab | y | 0.2 | 0.3
PCB controller | design | y | 3.25 | 4 |  |  | 80.25 | 47.65
PCB hand | wiring eagle | y
DC motors | test they work | y |  |  |  |  | 103.9 | 272.55
Wrist motor | Working 1 way coms with arduino | y
Digital Twin | Comunication protocall working | y | 3 | 5
Digital Twin | Conceptual design | y | 3 | 5
Digital Twin | Working | y | 10 | 18
CAD | put pressure sensors in design | y | 5 | 5
Build | Wire hand pcb | y | 7 | 15
Build | Wire controller PCB | y | 3 | 5
Build | Wire motors | y | 4 | 6
Control code | plan | y | 2 | 3
Control code | write frame work and get working | y | 15 | 22
Control code | PID for finger motor | y | 1.5 | 3 | 3
Control code | PID for tendon motor | y | 3 | 5 | 4
Control code | Combined finger and tendon motors | y | 2.5 | 4 | 5 |  | If the output to the base motor is negative and below a certain amount (ie above a certian mag) then set the tendon motor output to a slow reverse. May need to reset I part of tenodn motor afterwards
Control code | Improve code accuracy | y | 2 | 10
Ask Mahonri about cables for hand | lab things | y
CAD | fiddle with back of hand motor, is intersecting and needs another tie down hole | y
CAD | Forearm motors | y
CAD | Adjust wwrist motor mounting | y
CAD | Adjust back of hand for better wiring access | y
CAD | fix up finger model | y | 1 | 2
CAD | do rest of fingers | y | 8 | 10
Printing | reprint base of finger | y
Pirnting | print gear to attach to finger motor | y
Pressure sensors | Calibrate for force | y | 2 | 6
Hall sensors | Calibrate for angle | y | 2.5 | 4
Pots | Calibrate for angle | y | 0.75 | 2 | 2
CAD | Design sensors into thumb | y | 3 | 5
build | wire and build thumb | y | 3.5 | 5
Build | Wire upper arm motors | y | 5 | 7
Control Code | Calibrate upper arm motors | y | 3 | 5
Digital Twin | Link upper arm motors to digital twin | y | 8 | 13
Build modifications | Get larger springs or elastic or something | y | 2 | 5 | 6 | still to do on other hand
Build modifications | Cut away at base of fingers for tendon | y | 0.6 | 0.7
Hall sensors | Redo thumb angle calibration | y | 0.25 | 0.25
Electronics | rewire beradboard to perfboard | y | 2 | 3 | 1
Digital Twin | Get SW sensing of angles working | y | 1.5 | 2
Digital Twin | Decide on part moving method in SW | y | 1.5 | 3
Digital Twin | Get parts moving in SW | y | 3.5 | 7
Digital Twin | Build UI | y | 3.5 | 6
Digital Twin | Get fingertip sensing added | y | 4 | 6
Digital Twin | Get joint labels and info with SW text added (e.g. temp) | y | 0 | 4
Digital Twin | Improve capabilities | y | 10 | 15
Wiring | Wire and test 2 way coms on actual arms | y | 1 | 2
Report | Abstract | y | 0 | 0 |  |  | j
Report | Acknoledgements | y | 0.5 | 0.5 |  |  | jk
Report | Declaration of Authorship | y | 0.3 | 0.4 |  |  | jk
Report | Contents, figure list, table list | y | 1 | 1.5 |  |  | jk | Use chatgpt
Report | Project Outline | y | 0.5 |  |  |  | jk
Report | background | y | 1 |  |  |  | jk
Report | Lit review summarail | y | 5 | 10 |  | n | jk
Report | Design and Research Objectives | y | 0.5 | 4 |  | dn | jk
Report | take pic of servo modification | y | 0.2 | 0.2 |  | dn
Report | Fix up highlighted stuff | y | 3 | 6 |  | n
Report | Do figure and table labels | y | 1.6 | 3 |  | n | jk
Report | hall effect data | y | 0.75 | 1 |  | n
Report | finsh solidwokrs table and explanation | y | 1.5 | 2.5 |  | n
Report | write about sensor selection and finish table | y | 0.75 | 1 |  | n
Report | Do extra testing for sensors | y | 2 | 3 |  | dn
Report | Write about sensor accuracies | y | 4 | 6 |  | n
Report | grip force writing | y | 1 |  |  | n
Report | DT evaluation | y | 1 | 2 |  | n
Report | Finger accuracy | y | 2 | 3 |  | n
Report | PID effects on finger accuracy | y | 2 | 3 |  | n
| Conclusions and future work | y | 2 | 4 |  |  | last thing
| Measure things for jack | y | 0.5 | 0.5 |  |  | k
| Add appendices for code, pics, github? eagle files | n
| Accuracy Evaluation and recomendations | y | 1 | 2
| Add lit reviews to appendix | y
| refrences | y
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n